## Summary
| Rate Per hour | 32 | CAD
# | Segment | Effort (Man Days) | Cost (CAD) | Legends used in effort estimation sheet |  | Count of Items
1 | Source code walkthrough* | 36 | 9216 |  | Simple Items | 38
2 | UI Development | 320.5 | 82048 |  | Moderate Items | 30
3 | UI Design | 61 | 15616 |  | Complex Items | 6
4 | API Development | 265 | 67840 |  | Highly Complex Item | 6
5 | Documentation | 12 | 3072 |  | R & D required. To be estimated later | 1
|  | Total | 177792 |  | New Items Added | 4
* | Source code walkthrough effort is required to understand the validations and business logic of implemented in current desktop application.

## Effort Estimation
Screens and Services | Story board | API Spec | Dev Team | Notes | Presentation C# files | Data Access C# files | Estimate Man days (UI) | Estimate Man days(API) | Estimate Man days(Design) | Estimate Man days(Source Code) | Comments (RSI) | Comments (MIRCOM) | Comments (RSI) | Comments (RSI)
Elevator | Y | N | Mircom |  | NA | NA | [7 empty] | All the points will be done by MIRCOM team (Developpement as well as Integration).
Elevator Command | Y | N | Mircom |  | NA | NA
Video Phone | Y | N | Mircom |  | NA | NA
Edit Video Phone Options | N | N | Mircom |  | NA | NA
PC Decision | N | N | Mircom |  | PCDecisionForm, PCDecisionCtrl | Dcard
Import Job Options | N | N | RSI |  | NA | Ddatabase, DRestoreBackup |  |  |  |  | 1. For Import, Is it from Exported file? 2. Will we need to export also. 3. Backup: How back up is currently happening. For in database back-up, we need to change the schema structure. Or backup will be through files. 4. SQL Job need to be executed for Import and backup. 5. Tasks will be : Export, Import, Restore and Backup. | Export is not needed because the database is in the cloud. Backup is not done by SQL server service but by custom code to save database data into job files. Restore is the reverse process. | This point is mentioned below. | OK
Configuration Menu and Navigations | Y | N/A | RSI |  | NA | NA | 4 |  | 1 |  | Need to add one blank page and menu after login. Then user can go to respective module (Site, Monitoring, Configuration etc.). | After selecting a site, it will go to the Monitoring dashboard of the site. Maybe we can add a button to the dashboard to jump to the Configuration page | Where to show this button ? Will it be as menu item button ? After moving to the configuration page, will it be a panel page, kindly confirm? | OK | 1
Panels | Y | Y | RSI |  | NA | DPanel | 6.5 | 3.5 | 1 | 1 | 1. Parent panels can be registered as cloud gateways if they support the cloud gateway feature. However the standalone Gateway device can only be used as a cloud gateway and it cannot have any panel as children. 2. Does IsCloudProxy defines the parent panels as cloudgateway panel. Will the database table panel column will be considered for it? | 1. Standalone gateway can have children, the functional spec needs to be updated. 2. IsCloudProxy is experimental and is used for something else. Need to add a new field IsCloudGateway to the panel table | Ok | OK | 2
Advanced Network Setup Pop-up | Y | Y | RSI |  | AdvancedNetworkForm | DNetwork | 2 | 2 | 1 | 0.5 | Does Insert/Update is required? | only Update is needed | OK | OK | 1
Firmware Upgrade Wizard Pop-up | Y | Y | RSI |  | NetworkFWUpgradeForm, NetworkFWFileSelForm | NA | 6 | 4 | 1 | 1 | 1. Will Cloud panel will come in the panel list? 2. How to show data in lobby and card access version dropdown value in step 2. 3. As per excel sheet, "Select version from dropdown lists. The list contain come from what firmware files are available in the server folders". Will it not come database? 4. Where in database we need to save values. 5. How progress bar will work. | 1. yes 4. no need to save another here 5. SignalR messages will tell the progress | 1. OK. 2. TBD 3. TBD 4. OK 5. Ok Only Single panel upgrade is mentioned in documents. What about multiple? Any change in wizard if only single panel upgrade is there? | On Single panel update, the configuration will be updated and on multiple panel update, framework will get updated. ****** No panel update will be done by RSI but will only update the database. MIRCOM team is responsible for panel updation process. (OK). ************ As discussed on call RSI is not going to implement the update panel configuration, it will be done by MIRCOM. | 3
Panels (Edit mode) | Y | Y | RSI |  | NA | DPanel | 4 | 2.5 | 0.5 | 0.5 |  |  | Can gateway panel become the child of any parent panel? | OK | 2
Add Panel/Edit Panel Pop-up | Y | Y | RSI |  | AddPanelForm, IPAssignerForm | DPanel | 3.5 | 3 | 0.5 | 0.5 | 1. If parent panel need to become a child then in edit pop-up, master node will same value as parent panel. (IP Address is enabled only if the Master node selection is (this is Master)IP Address is enabled only if the Master node selection is (this is Master)). 2. From where the Find button will get the IP address list. 3. From where Panel models can be taken. | 2. Details of the Find feature TBD, most likely from SignalR messages 3.Panel model is a fixed list |  | OK | 1
Lobby Panel Operations | Y | Y | RSI |  | TASLobbyPanelCtrl | DTASLobbyPanel, DDateTime | 20 | 14 | 2 | 1 | 1.Dropown values will come from Resource files? 2. How language handling will be done in message tab? | 1. Which drop down values? In general if it is a fixed list it can be hard coded. If the list can change then API may be needed 2. The languages on the message tab come from the database | 1. OK 2.OK | OK | 2 | ?
Lobby Panel Inputs/Outputs | Y | Y | RSI |  | InputOutputCtrl | DInputOutput | 4 | 2 | 1 | 0.5 | As per document, there are tabbing in input and output. How we decide its count? | The counts of inputs and outputs are fixed according to the panel type and model | OK | OK | 1
Lobby Panel Correlations | Y | Y | RSI |  | CorrelationCtrl | DCorrelation | 3.5 | 3 | 1 | 0.5 | If Custom is selected, a Custom button will appear. | there is a Custom selection in the dropdown list | OK | OK | 1
Lobby Panel Edit Correlations | Y | Y | RSI |  | CorrelationCtrl, CorrelationDetailForm, CorrelationCustomForm, CorrelationNanoForm | DCorrelation | 3 | 2 | 1 | 0.5 | If Custom is selected, a Custom button will appear. | there is a Custom selection in the dropdown list | OK | OK | 2
Card Access Panel Operations | Y | Y | RSI |  | CASReaderPanelCtrl | DCASReaderPanel, DDateTime | 9 | 6 | 1.5 | 0.5 | 1. Isn't lobby panel screen doesn't have left menu appear as top bar when viewed on mobile screen. 2. In general what is "Set as cloud gateway". 3. Add card screen is missing. Is it same as custom card format. 4. Set date and time disabled. 5. Operation have 2 screen with different behaviour (61 and 66) | Not sure what is the question 4. Set date and time button to be disabled | OK | OK | 1
Card Access Panel Custom Card Format | Y | Y | RSI |  | CustomCardForm, CustomCardGraphicCtrl | DCardFormat | 4.5 | 3 | 1.5 | 1 |  |  |  | OK | 2 | ? Has some graphics
Card Access Panel Access Points | Y | Y | RSI | Share the same code as Lobby Panel’s | AccessPointCtrl, AccessPointDetailForm | DAccessPoint | 5 | 3 | 1 | 0.5 | 1. What is Times, Door timers and Schedule as per document ? | Storyboard screen issue (blame Raj) | Screen will be taken from Desktop. | OK | 3
Card Access Panel Inputs/Outputs | Y | Y | RSI | Share the same code as Lobby Panel’s | InputOutputCtrl | DInputOutput | 4 | 3 | 1 | 0.5 | Does all tables contains same UI? | Not sure what is the question | OK | OK | 1 | ? Very similar to lobby
Card Access Panel Correlations | Y | Y | RSI | Share the same code as Lobby Panel’s | CorrelationCtrl | DCorrelation | 5.5 | 3 | 0.5 | 0.5 |  |  |  | OK | 1 | ? Very similar to lobby
Card Access Panel Edit Correlations | Y | Y | RSI | Very simple screen | CorrelationCtrl, CorrelationDetailForm, CorrelationCustomForm, CorrelationNanoForm | DCorrelation | 2 | 2 | 0.5 | 0.5 |  |  |  | OK | 2
Elevator Panel Operations | Y | Y | RSI |  | ElevPanelCtrl | DPanel | 3 | 2 | 0.5 | 0.5 |  |  |  | OK | 1
Touch Panel Operations | Y | Y | RSI | Share the same code as Lobby Panel’s | TASLobbyPanelCtrl | DTASLobbyPanel, DTouchScreenPanel | 16 | 13 | 2 | 2 | Is SET Date and Time is disabled ? | Yes, set date and time button to be disabled | OK | OK | 2
Touch Panel Inputs/Outputs | Y | Y | RSI | Share the same code as Lobby Panel’s, with 2 extra checkboxes | InputOutputCtrl | DInputOutput | 4 | 3 | 0.5 | 0.5 |  |  |  | OK | 1 | ? Very similar to lobby
Touch Panel Correlations | Y | Y | RSI | Share the same code as Lobby Panel’s | CorrelationCtrl | DCorrelation | 6 | 3 | 0.5 | 0.5 |  |  |  | OK | 1 | ? Very similar to lobby
Touch Panel Edit Correlations | Y | Y | RSI |  | CorrelationCtrl, CorrelationDetailForm, CorrelationCustomForm, CorrelationNanoForm | DCorrelation | 2 | 2 | 0.5 | 0.5 |  |  |  | OK | 2
Touch Panel Touch Screen | Y | Y | RSI |  | TouchScreenCtrl, | DTouchConfig | 2 | 2 | 0.5 | 0.5 |  |  |  | OK | 2
Touch Panel Touch Screen Edit Theme | Y | Y | RSI |  | TouchThemeForm | DTouchConfig | 7 | 5 | 0.5 | 0.5 | May Need R & D | Why? It is only a list of items, grouped by category | OK | OK | 4 | ?
Touch Panel Touch Screen Edit Video | Y | Y | RSI |  | TouchMediaCtrl, TouchMediaSelectionForm, TouchSingleVideoCtrl | DTouchConfig | 5 | 2 | 0.5 | 0.5 | What is the format and source of video? | Common formats such as Wmv, Mpeg, Jpeg, PNG, etc. | OK | OK | 3
Touch Panel Touch Screen Advertising | Y | Y | RSI |  | TouchAdvertiseCtrl, TouchAdvertiseTabCtrl | DTouchAdvertising | 3 | 2 | 0.5 | 0.25 |  |  |  | OK | 1
Touch Panel Touch Screen Advertising > Add Media File | Y | Y | RSI |  | TouchAdvertiseAddForm, TouchAdvertiseEditForm | DTouchAdvertising | 5 | 3 | 0.5 | 0.25 | Add/Edit is combined | Yes, same screen | OK | OK | 3
Touch Panel Touch Screen Advertising > Add Media File > Play Schedule | Y | Y | RSI |  | TouchAdvertiseListForm | DTouchAdvertising | 3 | 2 | 1 | 0.5 | Add/Edit/Delete is combined |  |  | OK | 2
Touch Panel Touch Screen Directory groups (Newly Added) | Y | Y | RSI |  |  |  | 4 | 2 | 1 | 0.5 | Add will open a pop up ? Or a suggestion of displaying list of group in master page and user can add/edit/view in popup after clicking on group row. | Pop-up to Add/Edit is fine | OK | OK | 6
Touch Panel Touch Screen More options (Newly Added) | Y | Y | RSI |  |  |  | 3 | 1 | 1 | 0.5 | 1. What is play button for? | Play button is now removed | OK | OK | 6
Touch Panel Touch Screen Languages |  | Y | RSI |  | LanguageEditForm | DLanguages | 5 | 3 | 0.5 | 0.25 |  |  |  | OK | 2
Touch Panel Touch Screen Admin Password | Y | Y | RSI |  | TouchPasswordForm | DTouchAdvertising | 1 | 1 | 0.5 | 0.25 |  |  |  | OK | 1
Touch Panel Touch Screen Customize Buttons | Y | Y | RSI |  | CustomButtonsForm, CustomButtonsControl | DTouchGUIObjects | 1.5 | 1 | 0.5 | 0.5 |  |  |  | OK | 1
People | Y | Y | RSI |  | ResidentGridCtrl | DResident, Dcard | 5 | 3 | 1 | 0.5 | 1.Is green arrow for send to panel | Yes | OK | OK | 2
People Add People | Y | Y | RSI |  | AddResidentsForm, AddCardsForm | DResident, Dcard | 3 | 2 | 0.5 | 0.5 | 1. Multiple people add pop-up window is not available. | Storyboard updated | OK | OK | 1
People Profile | Y | Y | RSI |  | ResidentDetailForm, CardDetailForm | DResident, Dcard | 4 | 2 | 1 | 0.5 |  |  |  | OK | 2
People Entry Phone | Y | Y | RSI | Can share component with Edit Credential Details screen | ResidentDetailForm, CardDetailForm, ElevatorForm | DResident, Dcard | 4.5 | 3 | 0.5 | 0.5 |  |  |  | OK | 1
People Credentials | Y | Y | RSI |  | ResidentDetailForm, CardDetailForm | DResident, Dcard | 5.5 | 3.5 | 1 | 0.5 | 1. What is the role of link action in cards as cards under people are by default linked. | Cards/Credentials are now separated from People. Use Links to link them togather | OK | OK | 2
People history (Newly Added) | Y | Y | RSI |  |  |  | 2 | 3 | 1 | 0.5 |  |  |  | OK | 6
People Edit Multiple People | Y | Y | RSI |  | ResidentDetailForm, CardDetailForm | DResident, Dcard | 5 | 3 | 1 | 0.5 | 1. Multiple people edit - on/off switch is missing | The switch is removed and replaced by a fixed column of checkboxes | Ok | OK | 3
People Import People | N | N | RSI |  | ResExcelImportCtrl, CardExcelImportCtrl | DResident, Dcard | 9 | 6 | 0 | 0.25 | Import people template. | TBD | TBD | OK | 2
Credentials | Y | Y | RSI |  | CardGridCtrl | Dcard | 3 | 2 | 0.5 | 0.5 |  |  |  | OK | 1
Credentials Add Credentials | Y | Y | RSI |  | AddCardsForm | Dcard | 2 | 2 | 0.5 | 0.5 |  |  |  | OK | 1
Credentials Edit Credential Details | Y | Y | RSI |  | CardDetailForm, ElevatorForm | Dcard | 4 | 3 | 0.5 | 0.5 | Is profile and Goto person open in Pop-up | See the functional description, section 4.4.34.1 | OK | OK | 2
Credentials Edit Multiple Credentials | Y | Y | RSI |  | CardDetailForm | Dcard | 2.5 | 2.5 | 0.5 | 0.5 | 1. Multiple people edit - on/off switch is missing | The switch is removed and replaced by a fixed column of checkboxes | OK | OK | 2
Credentials Import Credentials | N | Y | RSI |  | CardExcelImportCtrl | Dcard | 9 | 6 | 0 | 0.5 | Import Credential Template | TBD | TBD | OK | 2
Schedule | Y | Y | RSI |  | ScheduleCtrl | DSchedule | 2 | 2 | 0.5 | 0 |  |  |  | OK | 1
Schedule Details | Y | Y | RSI |  | ScheduleCtrl | DSchedule | 2 | 2 | 1 | 0.5 | 1. For deletion, one schedule section need to be selected which can be deleted then. 2. Time overlap is not allowed | Not sure what is the question | OK | OK | 1
Holidays | Y | Y | RSI |  | HolidayCtrl | DHoliday | 2 | 2 | 0.5 | 0 |  |  |  | OK | 1
Holidays Details | Y | Y | RSI |  | HolidayCtrl | DHoliday | 2 | 2 | 1 | 0.5 |  |  |  | OK | 1
Access Levels | Y | Y | RSI |  | AccessLevelCtrl | DAccessLevel | 2 | 2 | 0.5 | 0.25 |  |  |  | OK | 1
Access Levels Edit Details | Y | Y | RSI |  | AccessLevelCtrl, ElevatorForm | DAccessLevel | 4 | 2.5 | 1 | 0.5 | Delete Access level button will come at which place ? | Delete Access Level button added to storyboard | Ok | OK | 2
Floor Groups | Y | Y | RSI |  | ElevatorGroupCtrl | DElevatorGroup | 2 | 2 | 0.5 | 0.25 |  |  |  | OK | 1
Floor Groups Edit | Y | Y | RSI |  | ElevatorGroupCtrl | DElevatorGroup | 2 | 2 | 1 | 0.5 | Add/Edit floor group |  |  | OK | 2
Floor Groups Relay Labels and Schedules | Y | Y | RSI |  | ElevatorRelayLabelSetupForm | DElevatorGroup | 2 | 2 | 1 | 0.5 |  |  |  | OK | 2
Cameras | Y | Y | RSI |  | VideoCtrl, VideoFactory | DCamera | 2 | 2 | 0.5 | 0.25 |  |  |  | OK | 1
Cameras Edit Camera Server | Y | Y | RSI |  | VideoServerCtrl | DCamera | 2 | 4 | 0.5 | 0.5 | 1.Add,Edit and Delete combined 2. How the import will be done? | 1. No add, just Edit and Delete 2. Need to connect to the NVR server to retrieve Cameras then add to the list | 1. Ok 2. Ok | OK | 3
Cameras Edit Camera | Y | Y | RSI |  | VideoCameraCtrl | DCamera | 3 | 3 | 1 | 0.25 |  |  |  | Camera streaming will not be implemented. The effort of streaming is not included here. Camers streaming will be done later after the discussion on camera streaming on cloud. | 2 | ? Show live feed?
Cameras Edit Camera Association | Y | Y | RSI |  | VideoAssocForm | DCamera | 2 | 2 | 1 | 0.5 | What is the mean by pre/post time? | Duration of video footage of an event | OK | OK | 1
Reports Charts | Y | N | RSI |  | NA | NA | 5 | 6 | 0.5 | 0 | 1. What is the limit of saved chart? 2. Need to create a file or table to store saved charts. 3. Export Excel,CSV and PDF | No limit yet but a separate Saved Reports screen maybe needed | OK | OK | 2
Reports Charts Edit Chart Option | Y | N | RSI |  | NA | NA | 2 | 2 | 1 | 0.5 |  |  |  | OK | 2
Reports Event Log | Y | N | RSI |  | ReportViewForm | DEventLog | 3 | 4 | 0.5 | 0 | How this report will get saved ? Will the configurations will get saved? | Only the configurations are saved to the Reports table | Ok | OK | 1
Reports Event Log Options Pop-up | Y | N | RSI |  | EventReportForm | DEventLog | 3 | 3 | 1 | 0 | Need more information on "Update Events". | TBD | TBD | OK | 2
Reports Event Log Filters Pop-up | Y | N | RSI |  | EventFiltersForm | DEventLog | 2 | 2 | 0.5 | 0.5 |  |  |  | OK | 2
Reports Residents | Y | N | RSI |  | ResidentDirectoryReportViewer | Dresident | 3 | 4.5 | 0.5 | 0.25 |  |  |  | OK | 1
Reports Residents Options Pop-up | Y | N | RSI |  | ReportOptionsForm | Dresident | 5 | 4 | 1 | 0.5 | Need to discuss on Save Functionality |  |  | OK | 1
Reports Credential | Y | N | RSI |  | ResidentDirectoryReportViewer | Dcard | 3 | 4.5 | 0.5 | 0 |  |  |  | OK
Reports Credential Options Pop-up | Y | N | RSI |  | ReportOptionsForm | Dcard | 4 | 3 | 1 | 0.5 |  |  |  | OK
Reports People | Y | N | RSI |  | NA | NA | 3 | 4.5 | 0.5 | 0 |  |  |  | OK | 1
Reports People Options Pop-up | Y | N | RSI |  | NA | NA | 5 | 4 | 1 | 0.5 |  |  |  | OK | 1
Reports Paper Directory | Y | N | RSI |  | ResidentDirectoryReportViewer | Dresident | 3 | 4.5 | 0.5 | 0 |  |  |  | OK | 1
Reports Paper Directory Options Pop-up | Y | N | RSI |  | ResidentDirectoryOptionsForm | Dresident | 2 | 2 | 1 | 0.5 |  |  |  | OK | 1
Reports Panels | Y | N | RSI |  | NA | NA | 3 | 6 | 0.5 | 0 |  |  |  | OK | 2
Reports Panels Options Pop-up | Y | N | RSI |  | NA | NA | 3 | 2 | 1 | 0.5 |  |  |  | OK | 2
Tools Backup & Restore | Y | N | RSI | Same pop-up is used for Delete | BackupForm, AutoBackupManagerForm | DRestoreBackup | 7 | 8 | 1 | 1 | 1. While Importing a file, the file will be saved as backup file? As it is in cloud, wouldn't it go to storage? 2. What is meant by "Users will be able to select a job site or folder that was backed up to delete permanently from the server." 3. Need to discuss Autobackup ? It is a function/Job on Azure cloud? 4. As per document "If the site that is being restored is different from the current site, a warning will pop up and if continue, the current site will be switched to the selected site before restoring it." Need discussion on it? 5. Does compatibility check happen while restoring the old backup? 6. Will the site upon which backup is being restored should be preserved or overwritten? 7. Only backup folders will get deleted. If some backup is restored so while deleting , is it disabled or hidden? 8. Backup files and folders are authorised by user. What about permissions of it? | TBD for Auto Restore and Windows service will be required. User wise display of Backups |  | Auto update will be done by windows service. 1. Backup and Auto backup will be done by MIRCOM side. RSI team will need to updated the backup time and backup details in the database. 2. For Import and restore, RSI team will just need to store the Import ,Delete and Restore details in the database. Import,Delete and Restore will be done by MIRCOM side using these database values. | 4 | ? The code to save and restore file is already implemented inC#
Tools Backup & Restore Restore Site Pop-up | Y | N | RSI |  | NA | DRestoreBackup | [7 empty] | OK
Tools Change Password | Y | N | RSI |  | PasswordForm | DUserAdmin | 2 | 2.5 | 1 | 0.5 | Need discussions on it. |  | Ok | OK | 1
Tools User Management | Y | N | RSI |  | UserManagementForm | DUserAdmin | 2 | 2 | 0.5 | 0.25 | Need discussions on it. |  | Need discussions on it. | OK | 2
Tools User Management Edit User Pop-up | Y | N | RSI |  | UserManagementForm | DUserAdmin | 2 | 2.5 | 0.5 | 0.25 | Need discussions on it. |  | Need discussions on it. | OK | 2
Tools User Management Custom User Levels | Y | N | RSI |  | NA | NA | 2 | 2.5 | 0.5 | 0.25 | Need discussions on it. |  | Need discussions on it. | OK | 2
Tools User Management Edit User Level | Y | N | RSI |  | NA | NA | 2 | 2.5 | 0.5 | 0.25 | Need discussions on it. |  | Need discussions on it. | OK | 2
Tools Alerts | Y | N | RSI |  | AlertSetupForm | DAlertConfig | 2 | 1 | 0.5 | 0 |  |  |  | OK | 1
Tools Edit Alert | Y | N | RSI |  | AlertDetailForm | DAlertConfig | 2 | 2.5 | 0.5 | 0.5 |  |  |  | OK | 1
Tools Export | Y | N | RSI | Need more discussions | XMLExporter | NA | 1 | 4 |  | 0.5 |  |  | Need discussions on it. | OK | 4
User authentication and authorization services | N | N/A | RSI | Need more discussions | NA | NA | 5 | 8 |  |  | This is to use existing systems only and not addition of any new |  | Need discussions on it. Work on this will be impacted on Phase 2 code also. Need estimation on it. | As the current implementation is using JWT token , same will be appplied in phase 3. This is considered as risky item because currently we are not aware of future implementation of Identity server to be provided by MIRCOM. Assumption: Currently authentication is performed in application and no authorization. In case authorization is to be implemented, the effort may increase which will be estimated later based on the identity server implementation. | 4
Camera stream routing service | N | N/A | RSI |  | NA | NA |  |  |  |  | Need discussions on it. |  | Need discussions on it. | Estimations will be done separately as agreed by RSI and MIRCOM. This is R&D work which will be done by 2 persons (One from Media and one from Azure). | 5
[7 empty] | 320.5 | 265 | 61 | 36

## Bifurcate Tasks
Task Detail | UI Efforts (In Days) | API Efforts (In Days) | Comments (RSI)
Lobby Panel Operations
Options - Pages design integration and binding data, show selected data and top button (Ok, Cancel) | 2 | 1.5
Call - Page design integration, bind and show selected data.Mic and Speaker volume button need to create and this is complex to implement. | 3 | 1.5
Message- Page design integration, bind and show selected data implementation. Need to create custom editor for language support | 3 | 1.5
Phone Lines - Page design integration, bind and show selected data. | 1 | 1.5
Keyboard - Page design integration, bind and show selected data. | 2 | 1.5
Passcode - Page design integration, bind and show selected data. | 1 | 1
Date Time - Page design integration, bind and show selected data. | 2 | 1.5
Other Options - Page design integration, bind and show selected data. | 2 | 1.5
Validate,Save data in all the given event, integration and test functionality (8 Logical screens) | 4 | 2.5
Touch Panel Touch Screen Edit Theme
Design integration, bind data and create popup | 2 | 1
Import property | 1.5 | 1.5
Export Property | 1.5 | 1.5
Save, validate and test functionality | 2 | 1
Tools Backup & Restore
Back up | 1 | 2
Design integration, bind, delete and save data | 2 | 2
Restore popup to show folder structure, select file and given that file to API | 2 | 2
Import popup to show folder structure, select file and given that file to API | 2 | 2
Window application for auto backup |  | 0
People Import People
UI development to edit spreadsheet | 5
Validation on inputs | 2 | 2
Fill imported data and save data | 2 | 4
Credentials Import Credentials
UI development to edit spreadsheet | 5
Validation on inputs | 2 | 2
Fill imported data and save data | 2 | 4
Reports Panels Options Pop-up | 3 | 3
Now Access card report replace with credential report
Reports Credential | 3 | 4.5
Reports Credential Options Pop-up | 5 | 4
People Report
Reports People | 3 | 4.5
Reports People Options Pop-up | 5 | 4
Residents Report
Reports Residents | 3 | 4.5
Reports Residents Options Pop-up | 5 | 4
Card Access Panel Inputs/Outputs | 4 | 3 | We have given average time in Input/Output for panels.
Card Access Panel Correlations | 5.5 | 3 | We have given average time in Input/Output for panels.
Touch Panel Inputs/Outputs | 4 | 3 | We have given average time in Input/Output for panels.
Touch Panel Correlations | 6 | 3 | We have given average time in Input/Output for panels.
Card Access Panel Custom Card Format | 4.5 | 3 | There are no graphics present in this screen.
Cameras Edit Camera | 3 | 3 | Will show the live feed based on existing streaming.